USC Event Checklist

Months Pre-Event (depending on event size):

Coordinate with faculty coordinator(s) to establish all event expectations

Provide faculty coordinator(s) with Faculty Lead Info Sheet

Reach out to all speakers with Staff Speaker Contact Template, modified according to event

Put speakers in contact with Hub Administrative Team for airfare & accommodation needs

Submit Facilities Event Permit Application

Place any necessary large-scale orders (tables, flowers, linens, specialized AV, etc.)

Place any necessary small-scale orders (folders, swag bag needs, paper goods, etc.)

Set up RSVP system and online forms

Create promotional materials including RSVP information

Send out event information to faculty/students/other listservs

Weeks Pre-Event (depending on event size):

Confirm with speakers/Hub Administrative Team that airfare & accommodation are finalized

Contact all requested caterers and schedule and finalize deliveries

Continue to advertise event to faculty/students/other requested listservs

Send out event reminder emails to those registered (w/date reminder, parking info, etc.)

Day Before Event:

Confirm delivery time and plan and re-share contact information with caterer

Confirm delivery time and plan and re-share contact information with all other vendors

Finish collating folders or print-outs for faculty/speakers/guests

Send out final event reminder email to listservs

Send out final event reminder email to pre-registered guests (w/parking info, etc.)

Send out final event reminder email to speakers (w/request for presentations, etc.)

Compile all speaker presentations if possible, test AV

Print out copies of RSVP sheet, ready to mark

Generate and print speaker and attendee nametags

Prepare swag bags

Create hold/intermediary background slide

Day of Event:

PRE:

Bring all materials to event space at open of set-up window

Check on and prep room and seating, put up flyers on doors, etc.

Collect and set materials from all day-of vendors

Collect and set up catering

Set up and double-check all AV including light background music

DURING:

Turn off background music

Maintain general cleanliness of event space

Provide AV support throughout

Provide other support as needed

POST:

Give out swag bags

Make sure all visitors are taken care of and have clear next directions / faculty guides

Clean up catering and event space, bring supplies back to office(s)

Days After Event:

Wash and return any table linens

Transmit any stray reimbursement requests from visitors to Hub Administrative Team

Follow up consistently with Hub Administrative Team re: reimbursements & honoraria